## Issue Log
ACTION ITEMS
# | Description | Assigned to | Date Assigned | Priority (H, M, L) | Due Date | Date Complete | Status | Notes/Resolutions | On time | Late
1 | Acme to provide list of Molina SMEs who need to be at the Kick Off Meeting | Gary Schmaltz | 2012-02-02 | M | 2012-02-10 | 2012-02-10 | Closed | Sample agenda sent 11/9 | 1 | 0
2 | Set up a team meeting to review the vendor’s project schedule | GarySchmaltz | 2012-02-02 | M | 2012-02-10 | 2012-02-10 | Closed |  | 1 | 0
3 | MHT will send the revised project schedules to Acme | Gary Schmaltz | 2012-02-07 | H | 2012-02-12 | 2012-02-11 | Closed | Revised plans sent bto Acme | 1 | 0
4 | Create a SharePoint for storing project documents and materials | John Sanchez | 2//7/2012 | L | 2012-02-20 | 2012-02-11 | Closed | New URL: PVV and EPM Proejct Management Site | 1 | 0
5 | Acme will send out the final SOW to reviewed | Sonny Johnson | 2012-02-03 | M | 2012-02-06 | 2012-02-06 | Closed | SOW of received | 1 | 0
6 | Must determine if we are contracted and required to used Emdeon | Gary Schmaltz | 2012-02-03 | L | 2012-02-10 | 2012-02-10 | Closed | We are required by the Project Sponor to use the Emeon Claims system for billing. | 1 | 0
7 | Send copy of survey to HHSC and Provider Services before conducting survey | Sonny Johnson | 2/13/ | H | 2012-02-15 | 2012-02-15 | Closed | Provider Surveys were distributed the SDA Providers. We expext answers back by 2/17/2012. | 1 | 0
8 | Review EVV project with the ARC team | Tony Johnson | 2012-02-14 | M | 2012-02-21 | 2021-02-23 | Closed | Tony held a meeting discuss the Fucntional, and Prgram data with the MHT IT team. | 0 | 1
9 | Acme to send Program Data Document sample | Sonny Johnson | 2012-02-20 | H | 2012-02-21 | 2012-02-21 | Closed | Sent 2/20/2012 | 1 | 0
10 | Refine meeting notes and distribute | Gary Schmaltz | 2012-03-09 | L | 2012-03-12 | 2012-03-13 | Closed | Meeting Notes were distributed | 0 | 1
11 | Get detailed provider data including their geographic location and membership count | Gary Schmaltz | 2012-03-09 | H | 2012-03-17 | 2012-03-17 | Closed | Worked wih Proejct Sponsor to colletc this information, and the numbers wer eprovided to Acme | 1 | 0
12 | Send training and communication plan to Acme review | Sherry Meyer | 2012-03-09 | L | 2012-03-17 | 2012-03-17 | Closed | P:lan was submitted to Acme for their review. | 1 | 0
13 | Send a list of providers and their interfaces and contact info after survey is completed | Gary Schmaltz | 2012-03-09 | M | 2014-03-20 | 2014-03-21 | Closed | List of provider sent to Acme for user account setup. | 0 | 1
14 | Send sample information Molina can post on to provider portal link which tells them about Acme and the initiative. | Tony Johnson | 2012-03-09 | M | 2012-04-08 | 2012-04-08 | Closed | Sample data was reviewed and Project sponsor approved for distribution. | 1 | 0
15 | Acme to send Molina statistics on how many customer representatives are typically needed for the call centers. | Sherry Meyer | 2012-03-09 | M | 2012-04-15 | 2012-04-13 | Closed | Acem completed stastics ahead of schedule. | 1 | 0
16 | Molina to determine if Providers will participate in UAT. | Gary Schmaltz | 2012-03-09 | M | 2012-04-15 |  | Open |  | 0 | 0
17 | Acme to provide Molina with list of Roles/SPM Jurisdictional Roles and will also include Provider Roles. | Sonny Johnson | 2012-03-09 | H | 2012-04-23 |  | Open |  | 0 | 0
18 | Set up meeting to train provider services and contracts reps | Shery Meyer | 2012-03-09 | M | 2012-04-16 |  | Open |  | 0 | 0
19 | Create the process for how FVV Devices will be distributed by Molina & installed by the provider. | Tony Johnson | 2012-03-09 | M | 2012-04-30 |  | Open |  | 0 | 0
20 | Decide how the calls will be routed when we receive them in member services. Our customer service folks should be informed of the system. | Mindy Johnson | 2012-03-09 | M | 2012-04-30 |  | Open |  | 0 | 0
21 | Acme to update the Business Rules document to change MMIS to the Molina Systems (DAT & QNXT). | Sonny Johnson | 2012-03-09 | M | 2012-04-30 |  | Open |  | 0 | 1
22 | Acme to update the Business Rules document to change MMIS to the Molina Systems (DAT & QNXT). | Acme | 2012-03-09 | M | 2012-05-05 |  | Open |  | 0 | 0
23 | Acme and MHT to determine field permissions for Providers & what data Providers will be allowed enter to conduct their business (i.e. physicians, schedules, DNR, priority level in the event of an emergency) | Molina/Gary | 2012-03-09 | M | 2012-05-08 |  | Open |  | 0 | 0
24 | Molina to provide the 3 best phone numbers from Care Advance System. | Molina/Daniel | 2012-03-09 | L | 2012-05-08 |  | Open |  | 0 | 0
25 | Molina to Identify IT owner for the Error Log file from Acme; Acme to provide description of contents. | Acme/Molina | 2012-03-09 | M | 2012-05-08 |  | Open |  | 0 | 0
26 | Acme to provide FAQs to Molina for Training and to answer questons for Call Center; Any checklists for Post and Pre Go-Live actions, and Register sample forms for Provider registrations process. | Acme | 2012-03-09 | M | 2012-05-08 |  | Open |  | 0 | 0
27 | Determnine if FTP Server site for storage of EVV/SPM import files is secure and meets data protection for HIPPA | Daniel | 2012-03-09 | M | 2012-05-09 |  | Open |  | 0 | 0
[5 empty] | Total: | 16 |  | Totals: | 12 | 4
[8 empty] | Present on Time: | 75%
Note on F15: Donna Ramos: based on 1/5 EVV draft plans.